# TERMS OF REFERENCE

# for expert/s to produce two publications

# < Reference number: 881697 – EQUAL – REC-AG-2019>

# < Title of the Action: EQUAL – Towards closing the gender gap in balancing professional and private lives of employees (implemented by Ana and Vlade Divac Foundation)>

TERMS OF REFERENCE

1.	BACKGROUND INFORMATION

1.1.	Partner country

1.2.	Contracting authority

1.3.	Country background

1.4.	Current situation in the sector

1.5.	Related programmes and other donor activities

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS

2.1.	Overall objective

2.2.	Purpose

2.3.	Results to be achieved by the contractor

3.	ASSUMPTIONS & RISKS

3.1.	Assumptions underlying the project

3.2.	Risks

4.	SCOPE OF THE WORK

4.1.	General

4.2.	Specific work

4.3.	Project management

5.	LOGISTICS AND TIMING

5.1.	Location

5.2.	Start date & period of implementation of tasks

6.	REQUIREMENTS

6.1.	Staff

7.	REPORTS

7.1.	Reporting requirements

7.2.	Submission and approval of reports

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting authority

“EQUAL - TOWARDS CLOSING THE GENDER GAP IN BALANCING PROFESSIONAL AND PRIVATE LIVES OF EMPLOYEES” Project is carried out by Ministry without portfolio in charge of demography and Population Policy and Ana and Vlade Divac Foundation. The Project is supported by European Commission Rights trough Programme Equality and Citizenship Programme - REC Programme (2014-2020).

As a part of the project, Ana and Vlade Divac Foundation announcing the public call for Expert/s.

## Country background

In spite of recent legislative changes, gender inequality in Serbia still persists, and stereotypes, including women’s role in family care, perpetuated by mainstream media, reinforce it. In one of the key aspects of gender inequality, the “domain of time”, representing gender gap in work-life balance, Serbia’s score ranks below EU average.

The lack of support to women for attaining balance between their professional and private lives largely influences the other domains of gender (in)equality in Serbia – work money and power. Findings from the National gender equality strategy speak further of these discrepancies: only 35% of women in Serbia are employed, in comparison to 50% of men. 38% of citizens witnessed firing of women from their jobs because of pregnancy. Managerial positions are occupied by twice as many men than women, and 77,9% entrepreneurs are men. Even worse is the situation of women living in rural areas, due to deeply embedded traditional division of roles and all the housework left to their responsibility, on top of their intensive engagement in agricultural work. However, only 17.3% of women in rural areas are registered as farm owners, according to the same source. Although the disbalance between work and life is not solely gender- conditioned, women working less than full time do it mainly because they have to take care of their children or disabled relatives, while men do it out of the lack of work, or because they are in training. Family care and other family reasons are predominant causes behind women’s decisions to not look for work at all. What is more, the lack of work-life balance and its economic consequences also prevent women from having children, according to the Republic of Serbia’s Strategy of encouragement to increasing the number of births.

## Current situation in the sector

- Gender equality – the extent to which women and men face the same opportunities within families, workplace and society at large – is an important dimension of social development, since it reflects the level of respect of human rights and possibly points to sources of discrimination. A recent EC-supported study on gender equality in Serbia (Gender Analysis for Serbia) concluded that in spite of progress in harmonizing legislation with the international and EU standards, and of increased efforts to mainstream gender in all sectors, “gender inequalities still persist”. According EC Progress Report for 2019, the largest number of complaints to Equality Commissioner of the Republic of Serbia pertain to, inter alia, gender-based discrimination, while the role of media in perpetuating gender stereotypes is a concern.

- The multi-faceted phenomenon of gender inequality includes domains of work, money, time, knowledge, health and power, according to Gender Equality Index for the Republic of Serbia, prepared by Government Social Inclusion and Poverty Reduction Unit of the Government of Serbia. The “domain of time” includes the dichotomy of paid and unpaid work at home and the care for children and other members of the household, as well as dichotomy of work and leisure time. In view of the gap between men and women in the domain of time (work-life balance) Serbia ranks below the EU average by 17 points (48,7 of 100 points). According to data from National gender equality strategy of the Republic of Serbia, 95% of all women in Serbia spend 5,08 hours per day on housework, while men spend nearly 40% less – 2,58 hours, and also have one hour more of leisure time than women.

## Related programmes and other donor activities

- A recent study by the Cabinet of MDPP – Synchronizing Work and Parenthood – dealt specifically with the challenges in attainment of balance between professional and family lives and identified key concerns and limitations of both employees and employers in Serbia. The study analyses concrete measures to advance the work-life balance (flexible working hours, paid leave for child care, financial support to parents, day-care facilities etc.) – many of which are    already being implemented to various extent in Serbia. The key cleavage, noticeable throughout the study, can be described as conflicting goals – those of employers – who want to increase profit, market share, efficiency and productivity; and those of employees – who need to harmonize their professional and family duties, career stability and progress and workplace well-being.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The project will address obstacles in the way of gender equality in work-life balance: tacit public acceptance of this inequality, lack of knowledge about labour-related rights, lack of the sense of entitlement of employees, and women in particular, to ask that their rights are observed and that other, non-mandatory measures at employers’ disposal are put to work. The project will also address the reluctance of employers to engage in practices of support to employees’ work-life balance, and will reach out to local authorities, soliciting their participation in dealing with this problem.

Finally, the project will provide evidence for update of existing central-level policies regarding work-life balance.

## Purpose

The purposes of this contract are as follows:

- Expert/s will analyse the legal framework and practice, and produce the Manual for work-life balance for employees

- Expert/s will analyse the legal framework and practice, and produce the Manual for work-life balance for employers

## Results to be achieved by the contractor

- Expert/s will produce 2 results:

- the Manual for work-life balance for employees during the March and April 2020

- the Manual for work-life balance for employers during June and July 2020

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- To involve media representatives

- To involve relevant actors – employees, employers, CSO’s dealing with socio-economic and gender issues, chambers of commerce

- To involve representatives of central and local government

## Risks

- Unexpected political or socio-economic crisis or event that undermines the effects of the traditional and online media campaigns

- Unexpected natural events that would consume full attention of the public (floods, health, heat etc.) and lessen the campaigns’ impact

- Lack of interest of top managers in large companies that are important employers of women to participate at the info-session (working breakfast)

- Lack of interest of presidents of municipal councils and assemblies to take part in info-session

- Anti-gender attitudes in political, and social life

- Interest of employees to fight for their rights regarding work-life balance

# SCOPE OF THE WORK

## General

### Description of the assignment

Expert/s should analyse the legal framework and working rights of employees and employers in Serbia. Based on that expert/s should produce:

- Manual for work-life balance for employees app. 15-page long publication, practical guide for employees to their rights regarding work-life balance, in Serbian language.

- Manual for work-life balance for employers- App 15-pages long publication, practical guide for employers to supporting employees’ work-life balance; in Serbian language.

### Geographical area to be covered

Expert/s will cover the legal framework in Serbia.

### Target groups

Expert/s will analyse the legal framework, labour law and working rights of employees and employers in Serbia, with special focus on female employees.

## Specific work

Expert/s should produce two publications:

- Manual for work-life balance for employees

- Manual for work-life balance for employers

Expert/s is/are bound by a Declaration of Impartiality and Confidentiality to be signed before starting each phase of the assessment. If an assessor believes there might be a situation of conflict of interests, he/she must inform the Ana and Vlade Divac Foundation immediately. In addition, strict confidentiality is required from the experts involved in the implementation of this Contract, notably on the assessments of the project.

More specifically the purpose of the work is:

- Desk research of legal framework, labour law, legal practice and working rights of employees in Serbia

- Desk research of legal framework, labour law, legal practice and working rights of employers in Serbia

- Production of Manual for work-life balance for employees. Manual will contain articles of the law relating to the working rights of employees, which relate to establishing a better balance between private and professional life (e.g. paternity and maternity leave etc.)

- Production of Manual for work-life balance for employers. Manual will contain articles relating to benefits that employers have by law that will help establish better balance between private and professional life (e.g. tax benefits when employing women or members of marginalized groups etc.)

## Project management

### Responsible body

Project coordinator and Financial manager within Ana and Vlade Divac Foundation will be in charge for the contract procedure and communication with expert/s.

### Management structure

Project Coordination: Execution of project tasks and cooperation with project team, administrative duties, communication with organisations and individuals involved in the project, including cooperation with external evaluators (subcontractors), assistance in preparation of technical and financial reports for donors and other tasks as required; preparation of monthly, mid-term and final progress reports.

Financial management: Responsibility for all financial activities on this project (for each of the partners), including preparation of financial reports and collecting all data and documents required for financial reporting. Financial management will be carried out by financial officers of the both partners.

### Facilities to be provided by the contracting authority and/or other parties

Ana and Vlade Divac Foundation will provide additional information and contacts for the analysis.

# LOGISTICS AND TIMING

## Location

Expert/s will conduct a desk research of legal framework in Serbia. The research does not include traveling outside of Belgrade and meetings can be conducted as a Skype call.

## Start date & period of implementation of tasks

The intended start date is <30.03.2020.> and the period of implementation of the contract will be < 4 > months from this date. It is expected that the expert/s will be completed with the following deliverables due:

| Deliverables | Deadline |
| --- | --- |
| Manual for work-life balance for employees | 30th of April 2020 |
| Manual for work-life balance for employers | 31st of July 2020 |

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Expert team can consist one or more experts:

Qualifications and skills of expert/s

A university/master degree in Law. Ph.D. would be considered a strong asset.

General professional experience

- Knowledge of Labour law in Serbia

- Knowledge of position of the workers in Serbian society

- Work with worker’s unions, Peaceful resolution of labour disputes

Specific professional experience

- Minimum 10 years of relevant professional experience

- Previous experience in Labour Law

- Membership in domestic and foreign organizations

- Published articles and books related to domestic and international labour law

Skills and Competencies:

- Excellent analytical skills;

- Strong writing skills;

- Displays capacity to provide experienced advice on best practices;

- Possesses knowledge of inter-disciplinary development issues;

- Focuses on result for the client and responds positively to feedback;

- Good application of Results-Based Management;

- Good communication, coordination and facilitation skills;

- Consistently ensures timeliness and quality of work;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Demonstrates integrity by modelling ethical standards.

# REPORTS

## Reporting requirements

To summarise, in addition to any documents, reports and output specified under the roles and tasks of the assessors, the Contractor shall provide the following reports:

| Name of report | Content | Time of submission |
| --- | --- | --- |
| Manual for work-life balance for employees first draft | Manual will contain articles of the law relating to the working rights of employees, which relate to establishing a better balance between private and professional life (e.g. paternity and maternity leave etc.) | 10th of April 2020 |
| Manual for work-life balance for employees final version | Manual will contain articles of the law relating to the working rights of employees, which relate to establishing a better balance between private and professional life (e.g. paternity and maternity leave etc.) | 30th of April 2020 |
| Manual for work-life balance for employers first draft | Manual will contain articles relating to benefits that employers have by law that will help establish better balance between private and professional life (e.g. tax benefits when employing women or members of marginalized groups etc.) | 10th of July 2020 |
| Manual for work-life balance for employers final version | Manual will contain articles relating to benefits that employers have by law that will help establish better balance between private and professional life (e.g. tax benefits when employing women or members of marginalized groups etc.) | 31st of July 2020 |

## Submission and approval of reports

Qualified and interested candidates are asked to submit their applications via e-mail: tender@divac.com:

•	Letter of Interest containing the following information:

(i) Explaining why the candidate is the most suitable for the work

(ii) Provide a brief methodology on the approach to the work and how it will be conducted (max. 300 words)

•	Updated Curriculum Vitae (PDF format)

•	Financial offer – lump sum

•	List e-mail contacts of three referees

The subject of the email should be: EQUAL_ToR for expert_candidate's name.

The applicant must include a financial offer together with all other requested documents, taking into consideration the objectives of the assignment, the tasks to be performed and deliverables requested. Please note that the financial offer must include all costs with the maximum limit of 4.000,00 €.

Deadline for submitting the application is 27th March 2020.

The contract will be awarded to the tender offering best price / quality ratio in accordance with the principles of transparency and fair competition and taking care to avoid any conflict of interest.

The Manuals as a product of the contract must be submitted to the project manager identified in the contract. The project manager is responsible for approving the Manuals.