TERMS OF REFERENCE

for expert ("assessor") to assist in the evaluation of the project

<Reference number: EU-03-22>

<Title of the Action: “WB&T for EmploYouth”(implemented by Ana and Vlade Divac Foundation)>

TERMS OF REFERENCE

Table of contents

1.	BACKGROUND INFORMATION	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	5

2.1.	Overall objective	5

2.2.	Results to be achieved by the Contractor	5

3.	SCOPE OF THE WORK	5

3.1.	General	5

3.2.	Specific Activities	5

4.	LOGISTICS AND TIMING	7

4.1.	Location	7

4.2.	Start date and period of implementation	7

5.	REQUIREMENTS	7

5.1.	Assessors	7

5.2.	Application Procedure:	9

6.	REPORTS	9

6.1.	Reporting requirements	9

6.2.	Submission & approval of reports	9

# BACKGROUND INFORMATION

The overall objective of “WB&T for EmploYouth” is to contribute to strengthened regional cooperation, participatory democracies and the EU approximation process in the Western Balkans and Turkey in the area of youth employment. The intention of the Project is that: CSOs are recognised in governmental strategies or measures addressing youth unemployment as partners, especially in addressing the problem of NEET youth, women and marginalised groups, CSOs have routine access to decision-making processes relevant to youth employment and are engaged as direct service providers in order to reach out to NEET youth, improved policies are in place with measures aimed at empowering the NEET youth, and especially women and marginalised groups, local, grassroots CSOs are providing support to local NEET youth, share their experiences regionally, and coordinate communication messages with other; CSOs in increasingly address actions towards NEET youth and CSOs are contributing to awareness-raising to increase awareness of general population, stakeholders and youth.

“WB&T for EmploYouth” Project is carried out by five organisations Partners Albania for Change and Development (Albania), Prima (Montenegro), Youth Alliance – Krusevo (North Macedonia), Community Volunteers Foundation (Turkey) and Ana and Vlade Divac Foundation (Serbia).

Specific objectives:

- (SO1) To create informed and constituency-based solutions for improved youth employment policies in the WB&T

- (SO2) To increase capacities of CSOs to pilot and promote innovative solutions for improved employment of NEET youth in the WB&T

- (SO3) To increase engagement and influence of CSOs in raising public awareness on youth employment in WB&T

The main activities include:

(1) advocacy efforts comprised from extensive research which will provide for an evidence-based approach in proposing more favourable youth employment policies in the region, with special focus on the NEET youth (4 annual regional monitoring reports on policies affecting youth employment (Youth Participation Indexes), 5 National Baseline and 5 National Control Studies on NEET youth employment, 20 Policy Briefs on NEET youth);

(2) Capacity building and sub-granting to strengthen CSOs ability to pilot youth employment models for NEET youth at the local level, and shape economic environment for youth (100 local, grassroot CSOs’ technical and management skills increased, 50 CSOs are supported financially, 3,000 NEET youth in local communities and launched 50 innovative employment schemes, YBH4WBT network is expanded to 70 CSO members);

(3) Awareness raising aim at involving stakeholders in the improvement of NEET youth employment (good practice examples in youth employment is exchanged and promoted regionally among diverse stakeholders, multi-stakeholder dialogue is created between CSOs, CSOs and networks and all relevant stakeholders for improved youth employment, awareness of up to 500,000 young people and up to 2,000,000 general public on youth employment is raised).

Diagram 1:

Impact (based on OO): The action contributed to strengthening regional cooperation, participatory democracies and the EU approximation process in the Western Balkans and Turkey in the area of youth employment

Outcome (based on SO1): Informed and constituency-based solutions for improved youth employment policies in the Western Balkans and Turkey are created

Outcome (based on SO2): Capacities of CSOs to pilot and promote innovative solutions for improved employment of NEET youth in the Western Balkans and Turkey are increased

Outcome (based on SO3): Engagement and influence of CSOs in raising public awareness on youth employment in the Western Balkans and Turkey are increased

WORK PACKAGE 1:  ADVOCACY

WORK PACKAGE 2: CAPACITY-BUILDING AND SUB-GRANTING

WORK PACKAGE 3: AWARENESS RAISING

OUTPUTS:

- 4 annual regional monitoring reportson policies affecting youth employment are prepared – Youth Participation Indexes

- 5National Baseline and 5 National Control Studies on NEET youth employment are conducted with special attention to women and marginalised groups

- 20 Policy Briefs on NEET youth, with special attention to women and marginalised groups are prepared and advocated to

500 stakeholders

OUTPUTS:

- 100 local, grassroot CSOs’ technical and management skills for promoting youth employment and the situation of NEET youth are increased

- 50 CSOs are supported financially and through mentoring for strengthening the NEET youth, as they strengthened 3,000 NEET youth in local communities and launched 50 innovative employment schemes

- YBH4WBT networkis expanded to 70 CSO members andstrengthened to work in the area of youth employment

OUTPUTS:

- Good practice examples in youth employmentis exchanged and promoted regionally among diverse stakeholders

- Multi-stakeholder dialogue is created between CSOs, CSOs and networks and all relevant stakeholders for improved youth employment

- Awareness of up to 500,000 young people and up to 2,000,000 general public on youth employment is raised

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

To undertake the midterm evaluation of the “WB&T for EmploYouth” Project from 15.03.2020 until 30.09.2022 carried out by five organisations Partners Albania for Change and Development (Albania), Prima (Montenegro), Youth Alliance – Krusevo (North Macedonia), Community Volunteers Foundation (Turkey) and Ana and Vlade Divac Foundation (Serbia) and to make recommendations that might improve design and implementation of future implementation of the projects.

## Results to be achieved by the Contractor

- Assessor will carry out the midterm assessment of “WB&T for EmploYouth” in accordance with EU procedures and standards. The project has been implemented by 5 national organisations and 47 local organisations in Serbia, Montenegro, North Macedonia, Albania and Turkey.

# SCOPE OF THE WORK

## General

Assessor should assess relevance, efficiency, effectiveness, sustainability and impact of the project. All criteria should be rated using a six-point rating scale: 6: Highly Satisfactory, 5: Satisfactory, 4: Marginally Satisfactory, 3: Marginally Unsatisfactory, 2: Unsatisfactory and 1: Highly Unsatisfactory. All ratings given should be properly substantiated.

## Specific Activities

Assessor will produce one report of the “WB&T for EmploYouth” Project.

Assessor are bound by a Declaration of Impartiality and Confidentiality to be signed before starting each phase of the assessment. If an assessor believes there might be a situation of conflict of interests, he/she must inform the Ana and Vlade Divac Foundation immediately. In addition, strict confidentiality is required from the experts involved in the implementation of this Contract, notably on the assessments of the project.

More specifically the purpose of the midterm evaluation is:

-	To assess overall performance against the project objective and outcomes as set out in the

Project Documents and other related documents;

-	To assess the effectiveness and efficiency of projects;

-	To analyse critically the implementation and management arrangements of projects;

-	To assess the progress towards achievement of the outcomes;

-    	To list and document initial lessons concerning project design, implementation and management;

-	To assess project relevance to national priorities per each country;

-	To provide lessons learned and recommendations that will help to improve future implementation of the projects.

- Methodology

The evaluation approach has to respond to standard international practices in project evaluation, as well as practices in an evaluation of EU projects. The proposed steps in conducting the evaluation will be:

•	Review of project documentation, monitoring records and progress and other relevant reports;

•	Initial meeting with Project Team to agree on the specific design and methods for the evaluation, what is appropriate and feasible to meet the evaluation purpose and objectives. Agree on the evaluation questions that will need to be answered, given limitations of time and existing data;

•	Prepare Work plan with evaluation matrix;

•	Organization of interviews with key staff involved in the project implementation;

•	Discussions with members of the project team, donor (European Commission), national partners and project beneficiaries from Serbia, Montenegro, North Macedonia, Albania and Turkey to assess project's relevance and effectiveness of project implementation, take note of their perceptions of accomplishments and potentials for further development. Objectively verifiable data should be collected whenever available, to supplement evidence obtained through interviews and focus group discussions;

•	Prepare Draft Report with recommendations for improvement and present it to the Project Team for feedback;

•	Incorporate received feedback into the Evaluation Report;

•	Prepare the Evaluation Report.

A following set of information sources about the project will be made available to Assessors:

•	Project documents;

•	Monitoring reports;

•	Policy recommendations;

•	Key documents produced by the project.

# LOGISTICS AND TIMING

## Location

Assessor is obliged to evaluate project activities implemented in Serbia, Montenegro, North Macedonia, Albania and Turkey.

Evaluation doesn’t include traveling outside of Belgrade, international meetings can be conducted through online meeting tools.

## Start date and period of implementation

It is expected that the evaluation will be completed within 25 working days, with the following deliverables due:

| Deliverables | Deadline |
| --- | --- |
| Work plan and evaluation matrix prepared and accepted by Ana and Vlade Divac Foundation | 10 days upon signing the contract |
| Draft Evaluation Report and Recommendations presented to the Project Team, Implementing Partner and beneficiaries | 15 days before the deadline |
| Evaluation report with Executive Summary prepared and accepted by Ana and Vlade Divac Foundation | 5 days upon receiving comments from Foundation on the draft report |

Payments for the deliverables will be made in 2 instalments, upon billing by the consultant and subject to quality review, clearance and acceptance by Ana and Vlade Divac Foundation.

The criteria of utility, credibility, and relevance/appropriateness will be used for assessing the quality of the evaluation report:

- The report has to be written in clear language (English);

- The Executive Summary should be an extremely short chapter, highlighting the evaluation mandate, approach, key findings, conclusions and recommendations;

- The information in the report has to be complete, well-structured and well presented;

- The information in the report has to be reliable i.e. well documented and supported findings;

- The information in the report has to addresses priority or strategic information needs;

- Recommendations have to be concrete and implementable;

- National perspective has been taken into account.

# REQUIREMENTS

## Assessor

Evaluation must fulfil  the following requirements:

Education:

- A university degree in the project related field. MA would be considered a strong asset.

Work experience:

- Minimum 5 years of relevant professional experience, preferably in international/multilateral development context;

- Previous experience in project evaluation methodologies;

- Previous assignments in the role of relevant senior expert positions would be considered as an asset.

Knowledge:

- Knowledge of political situation in Western Balkans Region and Turkey

- Knowledge of youth policy in Western Balkans Region and Turkey

- Knowledge of EU, evaluation policy, norms and standards;

- Knowledge of M&E Methodologies;

Skills and Competencies:

- Excellent analytical skills;

- Displays ability to synthesize research and reach empirically based conclusions on related subject;

- Strong writing skills;

- Proven capacity to produce reports;

- Displays capacity to provide experienced advice on best practices;

- Possesses knowledge of inter-disciplinary development issues;

- Focuses on result for the client and responds positively to feedback;

- Good application of Results-Based Management;

- Good communication, coordination and facilitation skills;

- Consistently ensures timeliness and quality of work;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Demonstrates integrity by modelling ethical standards.

Personal qualifications:

- Ability to deliver when working under pressure and within changing circumstances;

- Consistently approaches work with energy and a positive, constructive attitude;

- Excellent interpersonal skills.

- Consistently ensures timeliness and quality of work;

- Excellent drafting and reporting skills;

- Demonstrates strong oral and written communication skills;

- Evidence of ability to express ideas clearly; to work independently and in team;

- Ability to summarize and systematize complex information;

- Focuses on results and responds positively to feedback.

Language:

- Fluency in English, knowledge of Serbian shall be considered as an asset.

## Application Procedure:

Qualified and interested candidates are asked to submit their applications in person or by post to the address: "Ana and Vlade Divac" Foundation, Ilije Garašanina 53a/7, 11000 Belgrade:

•	Letter of Interest containing the following information:

(i) Explaining why the candidate is the most suitable for the work

(ii) Provide a brief methodology on the approach to the work and how it will be conducted (max. 300 words)

•	Updated Curriculum Vitae (PDF format)

•	Financial offer – lump sum

•	List e-mail contacts of three referees.

The subject of the email should be: YBH_ToR for evaluation_candidate's name.

The applicant must include a financial offer together with all other requested documents, taking into consideration the objectives of the assignment, the tasks to be performed and deliverables requested. Please note that the financial offer must include all costs with the maximum limit of 11.000,00 €.

# REPORTS

## Reporting requirements

To summarise, in addition to any documents, reports and output specified under the roles and tasks of the assessors, the Contractor shall provide the following reports:

| Name of report | Content | Time of submission |
| --- | --- | --- |
| Evaluation of project | Achievements and obstacles for each country | March 15th, 2023 |
| Recommendations | Recommendation for future implementation of the project for each country | March 15th, 2023 |

## Submission & approval of reports

The contract will be awarded to the tender offering best price / quality ratio in accordance with the principles of transparency and fair competition and taking care to avoid any conflict of interest.

One signed copy of the report, as well as electronic version, referred to above must be submitted to the Project Manager identified in the Contract. The reports must be written in English. The Project Manager is responsible for approving the reports.

A standard document will be made available by the Contracting Authority