TERMS OF REFERENCE

For Technical support for 4 local municipalities on LAPs development

Reference number: Grant BTD-FY2022-1553

Towards gender equality in Serbia

(Implemented by Ana and Vlade Divac Foundation)

The project “Towards gender equality in Serbia/Ravnopravnost ne može da čeka” is implemented by the Ana and Vlade Divac Foundation and funded by Balkan Trust for Democracy, a project of the German Marshall Fund of the United States and the Royal Norwegian Embassy in Belgrade.

As a part of the project, Ana and Vlade Divac Foundation announcing the public call for Technical support for 4 local municipalities on LAPs development.

Proposed project represents an effort of the Ana and Vlade Divac Foundation to contribute to the reform process in Serbia and add to the efforts towards the EU negotiation, focused on Chapter 23 and fundamental rights of citizens. Project is focused on gender equality as a large filed of discrimination in Serbia, with the aim to contribute to the empowerment of women in Serbia, particularly as regards employment and occupation, which is constantly recorded as one of the main fields of gender discrimination.

Gender equality – the extent to which women and men face the same opportunities within families, workplace and society at large – is an important dimension of country development, since it reflects the level of respect of fundamental human rights and possibly points to sources of multiple discrimination. An EC-supported study -Gender Analysis for Serbia concluded that in spite of some progress in harmonizing legislation with the international and EU standards, and of increased efforts to mainstream gender in all sectors, “gender inequalities still persist”.

The EU's founding values include the respect for human rights in law and in practice. The 2020 EU report on Serbia’s progress, in relation to the Chapter 23, says that in the field of non-discrimination, there are many weaknesses in both legal environment and in practice. As stated, the adoption of amendments to the law on anti-discrimination is seriously delayed, while the anti-discrimination strategy has not yet been renewed, although it has expired three years ago. The 2019 United Nations Committee on the Elimination of Discrimination against Women CEDAW report invited Serbia to take further steps in adopting the announced Law on gender equality, to take measures to strengthen the direct implementation of the UN Convention and the knowledge of the judiciary in this regard. In addition, both CEDAW report and the EU Report on Serbia for 2020 raised concerns over the division of responsibility between the various ministries, and the government body for gender equality that are overlapping in many fields related to gender equality. Furthermore, an efficient institutional set-up with adequate resources needs to be ensured, both in people and in means. At the local level, and based on the experience from the previous projects, the main policy issues rise from the lack of gender sensitive data, especially those related to the employment. Consequently, local action plans for gender and for the employment and measures designed on these data are based on national policies, not on the needs and constraints of the local groups of women. These are particularly visible when it comes to the most vulnerable groups such as Roma women, rural and women with disabilities, single mothers, and other. Additional effort must be invested in supporting the local authorities in collecting gender sensitive data, designing the local gender action plans and related indicators. This project is step forward in that direction.

Local authorities and their representatives need to better comprehend the role they play in ending women discrimination and fighting gender gap, based on study evidence, and monitoring report, along with capacity building and exchange with other municipalities that are the examples of good practices, that will further impact local policy measures and contribute to the attainment of the gender balance in the local communities. They also need to have a broader understating of the EU accession process and will be able to contribute to the development at local level and have fully integrated gender perspectives into local action plan (LAP) for employment as a first step forward in advancing local gender policy setting.  Study of local legal and policy framework will include 4 municipalities: Pirot, Zajecar, Apatin, Sombor.

### Description of the assignment:

Within the scope of the Project, the Study on comparative analysis on 4 local action plans for employment and gender equality, that precedes the technical support for 4 local municipalities on LAPs development, will determine the extent to which gender-sensitive statistics are used in the analysis of the local labor market situation when collecting data and in the analysis of gender inequality. The Study will also determine the extent to which local employment policies consider differences in the positions of women and men, that is, whether these policies contain gender sensitive goals and actions and the impact of the proposed interventions on the position of women and men in the labor market. Data collection will be conducted through a questionnaire to representatives of local mechanism for gender equality and questionnaire for representatives of office for local economic development to examine the level of cooperation and the implementation of measures related to the advancement of women in the labor market.

After the competition of the Study on comparative analysis on 4 local action plans for employment and gender equality, all 4 participating municipalities will be introduced with the findings and recommendations for improvement of their respective LAPs in a form of consultation meetings.

### Technical support will be offered for all 4 participating local municipalities, based on the results of the Study, information from the consultation meetings, and particular municipal needs for modifications and/or introduction of policy recommendation into the LAPs. Selected Consultant will be appointed to provide tailor-made technical support for each of participating municipalities in revising or developing LAPs with full integration of gender perspective. Technical support of 27 days is expected including filed visits, meetings and online consultations.

As a result, the technical support will provide plans for all 4 municipalities how to fully integrate gender perspectives into their employment LAPs.

## Start date & period of implementation of tasks

The intended start date is 15.10.2021. and the period of implementation of the contract will be 27 expert days during the period from 15.10.2021. until 15.03.2022. It is expected that the technical support for 4 local municipalities on LAPs development will be completed with the following deliverables due:

| Deliverables | Deadline |
| --- | --- |
| 4 plans for all 4 municipalities how to fully integrate gender perspectives into their employment LAPs | 15.03.2022. |

Reports:

Contractor shall provide complete narrative report on completed tasks of until 15th of March 2022.

Qualifications and skills of a Technical Support Consultant

Advanced university degree and experience in strategic planning processes.

Specific professional experience

- Minimum 10 years of relevant professional experience

- Profound understanding of legal procedures and local policy issues

- Strong background on gender equality and gender mainstreaming

- Experience in strategic planning and organisational development

- Knowledge of gender mainstreaming procedures

- Published writing and participation in the development of a large number of publications

Skills and Competencies:

- Excellent analytical skills;

- Strong writing skills in both Serbian and English;

- Displays capacity to provide experienced advice on best practices;

- Possesses knowledge of inter-disciplinary development issues;

- Good application of Results-Based Management;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Demonstrates integrity by modelling ethical standards.

Qualified and interested candidates are asked to submit their applications via e-mail: tender@divac.com:

•	Letter of Interest containing the following information:

(i) Explaining why the candidate is the most suitable for the work

(ii)Provide a brief methodology on the approach to the work and how it will be conducted (max. 300 words)

•	Updated Curriculum Vitae (PDF format)

•	Financial offer

•	List e-mail contacts of three referees

The subject of the email should be: TGES_ToR for technical support- candidate's name.

The applicant must include a financial offer together with all other requested documents, taking into consideration the objectives of the assignment, the tasks to be performed and deliverables requested. Please note that the financial offer must include all costs (including travel costs, communication costs and other costs that may occur during the task).

Deadline for submitting the application is 10.09.2021.

The contract will be awarded to the tender offering best price / quality ratio in accordance with the principles of transparency and fair competition and taking care to avoid any conflict of interest.

Technical support for 4 local municipalities on LAPs development is bound by a Declaration of Impartiality and Confidentiality to be signed before starting each phase of the assessment. If an assessor believes there might be a situation of conflict of interests, he/she must inform the Ana and Vlade Divac Foundation immediately. In addition, strict confidentiality is required from the experts involved in the implementation of this Contract, notably on the assessments of the project.